Welcome to XP Game

Vera Peeters
TRYX bvba
Pascal Van Cauwenberghe 
NAYIMA bvba

The Goal

We will simulate the XP Planning Game

  - Estimate user stories

  - Plan Releases

  - Perform implementation

  - Feed back

We will measure and use Velocity

Everyone gets to play Customer and Developer

Don't worry... implementation is not too difficult

Releases

A Release =

  - Customer writes stories

  - Developers estimate stories

  - Customer plans release

  - For each story in the release

    - Developers implement story

    - Customer performs acceptance tests

  - Debriefing and retrospective

We will play 3 releases

The Game

Play in teams

  - Four to six players per team

  - Developers & Customers & Managers

Each team has one coach

  - Runs the game and helps team

Earn Business Value by implementing stories

  - Team with highest Business Value wins

The Means

User Stories on index cards

Every Story is worth some Business Value...

  - ...but only if Story is implemented fully

Time is limited!

Developers Estimate

Estimate Story implementation effort

  - (easy) 1..2..3..4..5..6 (hard)

  - Or impossible

Order the Stories: Easy => Hard

Simplest Story = 2 effort points

Estimate other Stories relative to previous Stories

Ask your Coach (Customer) about the stories

Customer Plans Release

How many stories per release (180 sec)?

  - Estimate how long simplest story will take = X sec

  - (180 sec / X sec) * 2 Effort Points = Y points per release

Choose stories

  - Total # of Effort points <= Y points

Prioritize Stories...

  - ... to maximize potential Business Value

Developers Implement Stories

Take the first story from the release plan

  - Start timer

  - Implement Story

  - Stop timer

  - Coach (Customer) verifies  implementation

Until the hourglass is empty (180 sec)

Review progress in mid-iteration

If a story goes badly, you may abandon it...

  - ... if your Customer agrees

Enough Talk!

Now YOU can play!

You have 40 minutes

  - To estimate

  - To plan

  - To implement

So.... Get Busy!

What did we learn?

Estimates vs Actuals

  - Fixed Release length (1 hourglass)

  - Estimated we could do Y effort points

  - Actually, we implemented N effort points

VELOCITY = effort points per release

For your next release

  - Choose stories up to VELOCITY points

  - To be ready within the fixed Release length

Second Release

Planning Game and execution again

  - But now we know our velocity

Customers choose stories for a total of

VELOCITY effort points

Estimate consistently

  - Lay out the stories ordered by effort

  - Assign points by comparing with implemented stories

Stories can be re-estimated

Third Release

And again...

  - Estimate

  - Plan

  - Implement

OFF YOU GO!

Wrap up

Roles and Responsibilities

  - Customers

  - Developers

Estimating

  - Accuracy

  - Consistency

Releases

  - Measure Velocity => better estimates

  - Deliver Business Value

And The Winner Is...

And The Winner Is....

the team with the 
highest earned Business Value... 

They will win one of our fabulous prizes!

Exciting, isn't it?

Let's see the scores!